## Estimations - Summary
Initiative Name High Level Estimates - Summary
Total Effort (In Man Days) | 366
# Sprints | 5.65
# Resources | 10

## Estimations - Detailed
Initiative Name High Level Estimates - Detailed | [12 empty] | Team |  | In Sprints
Requirement ID | Requirement | Sub Requirements | Front End T-Shirt | Back End T-Shirt | DevOps T-Shirt | QA T-Shirt | Front End | Back End | QA | Dev Ops | Depedendant on Requirement ID | Total | Team | FE+BE | Front End | Back End | Sprints
1 | Requirement1 |  | M | S | XXS | XXS | 21 | 13 | 5 | 5 |  | 44 | Team 1 | 34 | 1 | 1 | 1
2 | Requirement2 |  |  | XL |  |  | 0 | 55 | 0 | 0 |  | 55 | Team 2 | 55 | 0 | 2 | 2
3 | Requirement3 |  | XXS |  |  |  | 5 | 0 | 0 | 0 | 7 | 5 | Team 3 | 5 | 1 | 0 | 1
4 | Requirement4 |  |  | XS |  |  | 0 | 8 | 0 | 0 | 3 | 8 | Team 1 | 8 | 0 | 1 | 1
5 | Requirement5 |  |  | L |  |  | 0 | 34 | 0 | 0 | 3 | 34 | Team 2 | 34 | 0 | 1 | 1
6 | Requirement6 |  | L |  |  |  | 34 | 0 | 0 | 0 | 2 | 34 | Team 3 | 34 | 1 | 0 | 1
7 | Requirement7 |  |  | XXXS |  |  | 0 | 3 | 0 | 0 | 1 | 3 | Team 1 | 3 | 0 | 1 | 1
[7 empty] | 60 | 113 | 5 | 5 |  | 183
|  | No of Resources |  |  |  |  | 4 | 4 | 1 | 1 |  | 10
|  | Inflation Rate | 2 |  |  |  | 120 | 226 | 10 | 10 |  | 366
|  | No of Days in Sprint | 10
|  | No of Sprints |  |  |  |  | 3 | 5.65 | 1 | 1 |  | 5.65
Note on H13: subramanyam.shankar: Enter the number of FE Resources
Note on I13: subramanyam.shankar: Enter the number of BE Resources
Note on J13: subramanyam.shankar: Enter the Number of QA resources. QA can be left blank.
Note on K13: subramanyam.shankar: Enter the number of Dev Ops resources. This is an optional field can be left blank.

## T-Shirt Sizing
Size | Days
XXXS | 3
XXS | 5
XS | 8
S | 13
M | 21
L | 34
XL | 55
XXL | 89
XXXL | 144
XXXXL | 233

## TeamSummary
Row Labels | Sum of FE+BE
Team 1 | 45
Team 2 | 89
Team 3 | 39
Grand Total | 173

## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Requirement1 | 1 | 1 | 1 | 1 | 25%
Requirement2 | 1 | 2 | 1 | 2 | 100%
Requirement3 | 2 | 1 | 2 | 1 | 35%
Requirement4 | 3 | 1 | 3 | 1 | 10%
Requirement5 | 3 | 1 | 3 | 1 | 85%
Requirement6 | 4 | 1 | 4 | 1 | 85%
Requirement7 | 4 | 1 | 4 | 1 | 50%

## Team Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | SPRINTS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Team 1 | 1 | 1.125 | 1 | 1.125 | 25%
Team 2 | 1 | 2.225 | 1 | 2.225 | 100%
Team 3 | 1 | 0.975 | 1 | 0.975 | 35%